## testing
Sr. No. | Bug No. | Bug decription | reported date | test procedure | Master or Slave | Modified HW/SW version | tester name | Testing location | resolution | resolved date | Dev. Name | Modified HW/SW version | tester's remark | Status
1 |  | we were unable to use variables from one .h file at different .c files |  |  | Slave |  | Priyanka | office | The solution for this problem which we found
| SW1 | it was giving duplication error. | 2022-02-15 |  | Master | V1.0.0 | Priyanka |  |  | 2022-02-21 | Prashant |  | Ok | Resolved
|  |  |  | Give +24v Power to J6 Connector 110v,19v,20vac to J26 connector ,connect remaining connector to slave PCB ,check on multimeter we get proper voltage on PCB or not then led gets turn ON indicating that PCB gets the power,check CAN communication led are blinking or not,check CAN,Vibrator,ADC,stepper motor work properly or not |  |  |  |  | #ifndef DELAY_VARIABLES_H_ // system generated #define DELAY_VARIABLES_H_ // system generated #ifndef DELAY_VAR // user defined # define _DELAY extern // user defined # define _DELAY_INIT(x) // user defined #else // user defined # define _DELAY // user defined # define _DELAY_INIT(x) = x // user defined #endif // user defined _DELAY _Bool msflag; // user defined _DELAY unsigned int mS_Cnt; // user defined _DELAY volatile _Bool ms100_flag; // user defined #endif /* DELAY_VARIABLES_H_ */ // system generated
2 | SW2 | Vibrator was operating for too much | 2022-02-15 |  |  | V1.0.0 | Priyanka | office | Added Math.h in main file and condition is written in code that if no. of cycles | 2022-02-21 | Prashant |  | OK | Resolved
|  | extra time and with extra cycles. | [6 empty] | is greater than defined or provided value then make it '0'.
|  | observation was the no of cycles were | [6 empty] | if(VBT_Cntr>VBRT_Cyl){
|  | increased for garbage value. | [6 empty] | VBT_Cntr = 0;}
3 | SW3 | while in run operation Weights of some | 2022-02-24 |  |  | V1.0.0 | Priyanka | office | Condition is added for this also that if settle time is greater than set value then | 2022-03-23 | Prashant |  | OK | Resolved
|  | heads were showing '0' and hence | [6 empty] | make it zero.
|  | recharge command was getting sent | [6 empty] | if(Settle_TMR > Settle_Time ){
|  | from master to that slave and it was | [6 empty] | Settle_TMR = 0;}
continiously doing the recharge resulting
weight bucket was getting full and
material was getting out from bucket.
4 | SW4 | Can communication is getting Off/not | 2022-03-07 |  |  | V1.0.1 | Priyanka | office | Still Working on it and below is the list of different trials taken so far. | 2022-03-23 | Prashant |  | OK | Resolved
responding after 20-21 minutes of
|  | operation. | [6 empty] | 1.tried chenging "timestamp_src" value and "timestamp_div" value
2.tried with low can speed it was 500kbps changed it to 34kpps
3.tried to reinitialize can when global error occurs.
4.tried avoiding checking can status
5.changed time stamp value to 1,2,4,8 initially it was 16(system generated)
6.changed receive mail boxex from 4 to 16
7.disabled error interrupts
8.changed value of global control register bit timestamp counter reset
9.tried commenting the clear messege ready instruction
10.tried changing RTBO value to 1 i.e. if bus is getting off then it will force fully
gets out of that mode.
11.Compared with old code and made the changes but still faced same issue.
12.when system was getting stopped then we were primaryly focusing on CAN
communication for that we were adding break point at receive isr of can but it was
not getting stuck there so because of that we were only focused on CAN.
but as we were stuck and tried with lots of possible option we decided go ahead
with code and for that we did put break point at run operation function code in
process can where we found out that after system stopped working it is observed
that can frames were getting received at that point.so problem was something
different.
→after that we monitored the run operation flags it is observed that when can
frame was received then its value was not getting changed to desired value.
so after further monitoring we came to know that the variable which is used
to decide slave id is getting some garbage value and the same variable is used to
extract data from can frame by left shiftting with slave id and hence as it was
extract data from can frame by left shiftting with slave id and hence as it was
→to get over this problem we written some logic to avoide garbage value in variable
but it didn’t work.
→so after that we decided to just switch on the system and do nothing and
monitored the variables which were getting garbage value but after running for 1 hour
it doesn’t affected the variables values.
→after that we decided to send only tare command which includes sending and
receiving of can frame i.e. full duplex communication it also worked fine for long time
(30 min) without affecting the variables values.(each command sent after every 1sec)
Unresolved
|  | After 20 min stepper motor stop |  |  | Slave |  |  | Office |  |  | Prashant |  |  | Unresolved | Testing inprogress
|  |  | 2022-03-22 |  |  | V1.0.2 | Priyanka |  | merg old/new stepper code |  |  | V1.0.3 |  |  | Resolved
|  | After 20 min stepper motor stop |  |  | Slave |  | Priyanka | Office | [5 empty] | Unresolved
|  |  | 2022-03-23 |  |  | V1.0.3 |  |  | Compare Old/new stepper Code |  | Prashant | v1.0.4
5 | SW5 | After 20 min stepper motor stop&Vibrator not working |  |  | Slave |  | Priyanka | Office | [5 empty] | Unresolved | Master
|  |  | 2022-03-24 |  |  | v1.0.4 |  |  | Commented the PMR.BYTE line in port.c file for portb and port 2 | 2022-03-28 | Prashant | v1.0.5 | OK | Resolved | Slave
|  | After 20 min stepper motor stop |  |  | Slave |  | Priyanka | Office
|  |  | 2022-03-25 |  | Slave | v1.0.5 |  | Office | All variables Initial values set to Zero or Non Zero. | 2022-03-31 | Prashant |  | OK | Resolved | Priyanka
Chaitanya
6 | HW1 | vreg pin of Tb6600 IC is not cut ,some components are missing on pcb & some components are of different value are solder on PCB | 2022-03-27 |  | Slave |  | Priyanka | Office |  | 2022-03-30 | Prashant |  | Ok | Resolved | Nana
7 | HW2 | Stepper Motor not rotate on new Slave PCB | 2022-04-04 |  | slave | v1.0.5 | Priyanka | Office | Use 22 pf capacitor across crystal because of clock issue,connect 104 Disc capacitor to Vreg pin (24) of TB6600 IC & give external 5v supply to stepper motor |  | Prashant |  |  | Unresolved | Dyaneshwar
8 | HW3 | Stepper Motor not rotate on new slave PCB | 2022-04-05 |  | slave | v1.0.5 | Priyanka | Office | Use 33 pf capacitor across crystal because of clock issue ,changes the crystal ,then check clk & enable signal is transmitted from controller to stepper motor correctly or not, that timing signal is transmitted from controller but it's not getting to motor |  | Prashant |  |  | Unresolved | Prashant
9 | HW4 |  | 2022-04-07 |  | slave | v1.0.5 | Priyanka | Office | Dry solder to transisitor of OPTO5 on slave PCB because of this dry solder ,clock was not getting to motor& then 47uf/63v capacitor is conncted to 24 pin of TB6600 IC | 2022-04-07 | Prashant |  | Ok | Resolved
10 | HW5 | No power isssue to 2 slave PCB ,Load Ptogram in 5 PCB but Adc & CAN Not working ,In 1 PCB program load ,CAN working but ADC not working,For 1 PCb load cell problem,For 1 PCB pin 2 of TB6600Ic is cut but in actual we need to cut pin 24 of TB6600 IC | 2022-04-08 |  | Slave | v1.0.5 | Priyanka | Office |  |  |  |  | NOT OK | Unresolved
11 | HW5 | ADC Problem | 2022-04-11 |  | Slave | v1.0.5 | Priyanka | Office | CAN Problem solved ,solder 8MHZ crystal to Y2 ,on PCB 4.9 MHZ crystal connected |  |  |  | NOT OK | Unresolved
For ADC, changes C13 ,C52,C74,C77 capacitor ,Inductor also ,changes C12,C6 capacitor in power supply section,C89,C25 Changres
On PCB Actual Required
C13 104 /1206 22nf
C52 22nf 104/1206
C74 1uf 104/1206
C77 1uf 104/1206
C12 Black 102 102
C6 Black 102 102
C89 Black 102 102/1206
C25 Black 102 102/1206
12 | HW6 | ADC Problem | 2022-04-12 |  | Slave | v1.0.5 | Priyanka | Office | ADC problem of 1 new PCB solved ,Stepper Motor ,CAN ,vibrator is also check,stepper is remaining |  |  |  |  | Unresolved
Instead of L4,L5 Inductor ,in actual on PCB 102 /1206 capacitor is soldered

## Master
Sr. No. | Bug No. | Bug decription | reported date | test procedure | Modified HW/SW version | tester name | resolution | resolved date | dev. Name | Modified HW/SW version | tester's remark | Status

## Slave
Sr. No. | Bug No. | Bug decription | reported date | test procedure | Modified HW/SW version | tester name | resolution | resolved date | dev. Name | Modified HW/SW version | tester's remark | Status